## Sheet1
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Rating | Mitigation Strategy | Owner
R001 | Errors in the calculation logic in the interest and loan features, thus leading to incorrect results in the balance or repayment total. | Functional | High | High | Critical | Boundary value analysis and formula verification against known PMT and compound interest results | Tester
R002 | No Insufficient fund checks or uncalled logic errors when withdrawing. | Functional | High | High | Critical | Decision table testing and extensive negative test cases for withdrawal scenarios | Tester
R003 | When user logs out the session might not be terminating correctly resulting in security concerns | Security | Medium | High | High | Authentication test cases and manual code trace of logout and token expiry logic | Tester
R004 | The system might allow an unauthorized user to make changes to an account or loan that shouldn’t be allowed | Functional | Medium | High | High | State transition diagrams and tests for all valid and invalid transitions | Tester
R005 | When multiple operations happen at the same time it could cause conflict with the data resulting in wrong results. | Functional | Medium | High | High | Transfer tests with rollback verification and Assert. Multiple checks on both accounts | Tester
R006 | Weak or missing input validation allowing null, empty, oversized or malicious inputs | Security | High | Medium | High | Enter bad and incorrect inputs to see if the program handles all types of input | Tester
R007 | Not enough of the code might actually be tested | Process | Medium | Medium | Medium | I'll keep checking how much code my test cases actual cover and fill in the gaps | Tester
R008 | Time pressure causes incomplete test design or skipped edge cases | Project | High | Medium | High | Strict adherence to the five-phase plan and prioritisation of Critical/High risk areas first | Tester
R009 | Fixing a problem might cause an issue somewhere else | Process | Medium | Medium | Medium | Full regression test run after every fix; maintain a regression suite of high-priority tests | Tester
R010 | Complicated rules in the transaction engine could be quite easy to misinterpret | Functional | Medium | High | High | Every possible combination of the rules will be written and I will manually check all the code follows them. | Tester
R011 | Performance of critical operations exceeds defined time thresholds | Non-Functional | Low | Medium | Low | Stopwatch-based performance tests with documented thresholds and recommendations | Tester
R012 | Some requirements might not have a test written for them | Process | Medium | Medium | Medium | Maintain and continuously update the Requirements Traceability Matrix throughout the project | Tester