## Defect Log
Defect ID | Title | Severity | Priority | Status | Module | Test Evidence | Steps to Reproduce | Expected Result | Actual Result | Root Cause | Fix Applied | Retest Result | Date Logged | Date Closed
DEF-001 | SA ID validation accepts invalid dates/checksums | High | P1 | Open | Validation Library | ValidationAggressiveCoverageTests; ValidationBranchCoverageTests | Validate 9913995009087 or an invalid checksum. | Invalid ID is rejected. | ID is accepted. | Validation returns true before day/checksum validation. |  |  | 2026-08-28
DEF-002 | Exact maximum amount is rejected | Medium | P2 | Open | Validation Library | ValidationTests; ValidationBranchCoverageTests | Validate 999999.99. | Maximum is accepted inclusively. | Validation returns false. | Maximum comparison uses < rather than <=. |  |  | 2026-08-28
DEF-003 | Simple interest uses ten-month annual conversion | High | P1 | Open | Interest Calculator | InterestCalculationTheories; InterestRequirementTests | Calculate simple interest for 1000 at 8% for 12 months. | Interest is 80.00. | Interest is 96.00. | Annual rate is divided by 10 instead of 12. |  |  | 2026-08-28
DEF-004 | FutureValue non-compound branch calculates compound interest | Medium | P2 | Open | Interest Calculator | InterestBranchCoverageTests; InterestCalculationAuditTests | Call FutureValue with isCompound false. | Principal plus simple interest. | Compound result is returned. | False branch calls CompoundInterest. |  |  | 2026-08-28
DEF-005 | New-account daily withdrawal limit derives from deposit | Medium | P2 | Open | Account Management | AccountCreationTests | Create Savings account with 500 deposit. | Savings daily limit is 5000. | Daily limit is 500. | Limit is assigned from initial deposit. |  |  | 2026-08-28
DEF-006 | Ineligible account states and negative balances can be closed | High | P1 | Open | Account Management | AccountClosureTests | Close dormant zero-balance or active negative-balance account. | Closure is rejected. | Closure succeeds. | Closure checks only positive balance and not Active status. |  |  | 2026-08-28
DEF-008 | Daily withdrawal total is never reset | Medium | P2 | Open | Transaction Engine | WithdrawalTests | Perform a withdrawal on a new day after previous daily use. | New-day limit is available. | Prior total remains accumulated. | No date-boundary reset exists. |  |  | 2026-08-28
DEF-009 | Transfer bypasses destination-status and daily-limit rules | High | P1 | Open | Transaction Engine | TransactionBranchCoverageTests | Transfer to closed destination or after source daily limit used. | Transfer is rejected. | Transfer succeeds. | Transfer lacks destination-status and daily-limit guards. |  |  | 2026-08-28
DEF-010 | Loan eligibility omits instalment and lacks income/debt validation | High | P1 | Open | Loan Processing | LoanBranchCoverageTests | Apply with zero income or negative existing debt. | Validation failure. | Division-by-zero exception or accepted application. | DTI divides existing debt by income only. |  |  | 2026-08-28
DEF-011 | Loan overpayment creates negative outstanding balance | High | P1 | Open | Loan Processing | LoanBranchCoverageTests | Repay 150 against 100 outstanding. | Balance is capped at zero. | Balance becomes -50. | Repayment amount is not capped. |  |  | 2026-08-28
DEF-012 | Early-settlement fee uses principal instead of outstanding balance | High | P1 | Open | Loan Processing | EarlySettlementTests; LoanBranchCoverageTests | Calculate settlement for 100000 principal and 50000 outstanding. | Settlement is 50750. | Settlement is 51500. | Fee is based on PrincipalAmount. |  |  | 2026-08-28
DEF-013 | Expired lockout is not cleared | High | P1 | Open | Authentication Module | AuthBranchCoverageTests | Set LockoutExpiry in past and log in with valid credentials. | Lock clears and login succeeds. | Login remains blocked. | Login never checks lockout expiry. |  |  | 2026-08-28
DEF-014 | Inactive sessions remain valid after logout | High | P1 | Open | Authentication Module | SessionTests; AuthBranchCoverageTests | Logout then validate same token. | Validation fails. | Validation succeeds. | ValidateSession does not check IsActive. |  |  | 2026-08-28
DEF-015 | Permissions granted to inactive or expired sessions | Critical | P1 | Open | Authentication Module | AuthBranchCoverageTests | Request Teller permission with inactive/expired token. | Permission denied. | Permission granted. | HasPermission does not validate session state or expiry. |  |  | 2026-08-28